## Dashboard
Invoice Parser — Corrected Post-M2.5 Dashboard
M0-M2 are complete and frozen. All newly selected open-source model/parser integration is M2.5. M3 fixture-driven UI work may overlap, but real M3 end-to-end completion requires M2.5.
Milestone | Status | Next action | Launch blocker | Metric | Value
M0 | COMPLETE | Maintain frozen pilot profile | NO | Remaining M2.5-M5 issues | 32
M1 | COMPLETE | Run contract regression on every change | NO | M2.5 issues | 8
M2 | COMPLETE_FROZEN | Maintain M2 provider contract and evidence links | NO | M3 issues | 8
M2.5 | NEXT | Snapshot M2 contract and add provider feature flags | YES | M4 issues | 9
M3 | PLANNED_PARALLEL | Build first review slice with fixture provider | YES | M5 issues | 7
M4 | PLANNED | Complete launch safety evidence | YES | Synthetic fixtures | 29
M5 | PLANNED | Run closed supervised pilot | NO | Quarantine fixtures | 4
M6 | DEFERRED | Choose one requested capability | NO | Ground-truth fixtures | 25
M2.5 First Smoke Slice | Fixture | Expected behavior | Done?
Digital PDF | INV-002 | Docling/native parse → canonical candidate | No
Multipage lines | INV-011 | Stable page/table extraction | No
Blurred scan | IMG-001 | OCR/evidence or safe quality warning | No
Rotated image | IMG-002 | Normalize orientation and extract | No
Ambiguous number | INV-016 | Preserve ambiguity; do not invent | No
Hybrid PDF | HYB-001 | Preserve completed M2 route decision | No
Unsafe PDF | BAD-001 | Reject safely without model call | No

## Milestone Status
Milestone | Status | Status Basis | Next Action
M0 | COMPLETE | Project owner status and M0 handoff | Maintain frozen pilot profile
M1 | COMPLETE | Project owner status | Run contract regression on every change
M2 | COMPLETE_FROZEN | Project owner status; no retroactive open-source scope | Maintain M2 provider contract and evidence links
M2.5 | NEXT | New post-M2 open-source integration milestone | Snapshot M2 contract and add provider feature flags
M3 | PLANNED_PARALLEL | Fixture-driven work may overlap M2.5; real E2E depends on M2.5 | Build first review slice with fixture provider
M4 | PLANNED | Blocked by M3 | Complete launch safety evidence
M5 | PLANNED | Blocked by M4 | Run closed supervised pilot
M6 | DEFERRED | Requires M5 demand evidence | Choose one requested capability

## Remaining Issues
Milestone | Issue ID | Title | Priority | Owner Role | Primary Docs | Acceptance Criteria | Dependencies | Status | Next Evidence | Notes
M2.5 | M2.5-01 | Freeze M2 provider contract and feature flags | P0 | Backend/AI | 18_M2_FROZEN_AND_M2_5_HANDOFF;23_M2_5_IMPLEMENTATION_PLAN | Existing contract tests pass; provider disable restores prior behavior | M2 | NOT_STARTED | Contract snapshot and rollback test
M2.5 | M2.5-02 | Digital PDF parser adapter | P0 | AI/Backend | 03_TECHNICAL_ARCHITECTURE;23_M2_5_IMPLEMENTATION_PLAN | Digital PDF fixtures produce reproducible page structure and provenance | M2.5-01 | NOT_STARTED | Docling/native parser fixture report
M2.5 | M2.5-03 | Scan layout OCR evidence adapter | P0 | AI/Backend | 19_OPEN_SOURCE_MODEL_STRATEGY;20_SYNTHETIC_CORPUS_GUIDE | Image/TIFF fixtures return OCR layout evidence or safe quality failure | M2.5-01 | NOT_STARTED | PaddleOCR-VL route report
M2.5 | M2.5-04 | Qwen canonical semantic extraction adapter | P0 | AI/Backend | 19_OPEN_SOURCE_MODEL_STRATEGY;invoice.schema.json | Supported fixtures return schema-valid candidates or explicit failure | M2.5-01 | NOT_STARTED | Qwen provider contract report
M2.5 | M2.5-05 | Compose local routes with provenance and idempotency | P0 | Backend/AI | 03_TECHNICAL_ARCHITECTURE;04_EXTRACTION_VALIDATION_SPEC | Replays are idempotent and every route/version is reproducible | M2.5-02,M2.5-03,M2.5-04 | NOT_STARTED | End-to-end route report
M2.5 | M2.5-06 | Benchmark synthetic and real corpora | P0 | Data/AI | 06_EVALUATION_TEST_PLAN;22_MODEL_BENCHMARK_RUNBOOK | 29 fixtures run; 25 ground truths scored; real holdout separate | M2.5-05 | NOT_STARTED | Benchmark scorecards
M2.5 | M2.5-07 | Bounded repair and safe model failure handling | P0 | AI/Backend | 04_EXTRACTION_VALIDATION_SPEC;22_MODEL_BENCHMARK_RUNBOOK | One field-scoped repair max; timeout/OOM/invalid output fail safely | M2.5-04,M2.5-05 | NOT_STARTED | Repair and failure tests
M2.5 | M2.5-08 | Select model configuration and approve rollout ADR | P0 | Architecture/Product | 10_ADRS;23_M2_5_IMPLEMENTATION_PLAN | Selected route documented; feature-flag rollback tested; M3 contract unchanged | M2.5-06,M2.5-07 | NOT_STARTED | ADR and rollback evidence
M3 | M3-01 | Document workflow and Solid Queue jobs | P0 | Backend | 03_TECHNICAL_ARCHITECTURE | State/idempotency tests pass | M2 | NOT_STARTED
M3 | M3-02 | Batch progress and risk queue | P0 | Fullstack | 02_PRD | Progress updates and risk sorting work | M3-01 | NOT_STARTED
M3 | M3-03 | Evidence-backed document editor | P0 | Fullstack | 04_EXTRACTION_VALIDATION_SPEC | High-risk fields focus evidence | M3-02 | NOT_STARTED
M3 | M3-04 | Locale format and pack override | P0 | Fullstack | 14_GLOBALIZATION_STRATEGY | Operator override audited | M3-03 | NOT_STARTED
M3 | M3-05 | Acceptance policy | P0 | Backend | 06_EVALUATION_TEST_PLAN | No critical/high auto-accept | M1-04,M2.5-06 | NOT_STARTED
M3 | M3-06 | Immutable revisions and audit | P0 | Backend | 03_TECHNICAL_ARCHITECTURE | Approved revision immutable | M3-03 | NOT_STARTED
M3 | M3-07 | Keyboard review workflow | P1 | Fullstack | 02_PRD | 50-document system flow passes | M3-03 | NOT_STARTED
M3 | M3-08 | Approved-revision export integration | P0 | Backend | OpenAPI;exports | Only approved revisions exported | M1-06,M3-06 | NOT_STARTED
M4 | M4-01 | Authentication and tenant isolation | P0 | Security/Backend | 05_SECURITY_PRIVACY | Cross-tenant tests fail closed | M3 | NOT_STARTED
M4 | M4-02 | Private object storage | P0 | Infra | 05_SECURITY_PRIVACY | Short-lived authenticated access | M2-01 | NOT_STARTED
M4 | M4-03 | Retention and deletion verifier | P0 | Backend/Infra | 07_OPERATIONS_RUNBOOK | All object classes reconciled | M4-02 | NOT_STARTED
M4 | M4-04 | Content-free logging proof | P0 | Security | 05_SECURITY_PRIVACY | Canary data absent from logs/errors | M2.5,M3 | NOT_STARTED
M4 | M4-05 | Quotas spend limits circuit breaker | P0 | Backend/Infra | 07_OPERATIONS_RUNBOOK | Ceiling pauses external calls safely | M2.5-05 | NOT_STARTED
M4 | M4-06 | Deploy web job database and backups | P0 | Infra | 03_TECHNICAL_ARCHITECTURE | Pilot environment healthy | M4-01,M4-02 | NOT_STARTED
M4 | M4-07 | Restore and recovery drills | P0 | Infra | 07_OPERATIONS_RUNBOOK | Evidence recorded and targets met | M4-06 | NOT_STARTED
M4 | M4-08 | Privacy residency launch approval | P0 | Security | 05_SECURITY_PRIVACY | Checklist signed | M0-07,M4-03,M4-04 | NOT_STARTED
M4 | M4-09 | Security CI and upload abuse suite | P0 | Security | 05_SECURITY_PRIVACY | Brakeman/dependency/upload tests pass | M4-01 | NOT_STARTED
M5 | M5-01 | First supervised 50-document batch | P0 | Pilot | Pilot Scorecard | Batch completes end-to-end | M4 | NOT_STARTED
M5 | M5-02 | Correction taxonomy and root causes | P0 | Data/Product | 06_EVALUATION_TEST_PLAN | Every correction categorized | M5-01 | NOT_STARTED
M5 | M5-03 | Two-week 500-document pilot | P0 | Pilot | Pilot report | Volume target completed | M5-01 | NOT_STARTED
M5 | M5-04 | Measure safety speed and cost gates | P0 | Data/Product | Workbook dashboard | Release metrics computed | M5-03 | NOT_STARTED
M5 | M5-05 | Regression after every change | P0 | Data/Engineering | Benchmark reports | Frozen holdout never bypassed | M5-02 | NOT_STARTED
M5 | M5-06 | Operator debrief and willingness to pay | P0 | Founder/Product | 09_BUSINESS_VALIDATION | Commercial signal recorded | M5-03 | NOT_STARTED
M5 | M5-07 | Go iterate stop decision | P0 | Founder | Decision record | Evidence-backed decision | M5-04,M5-06 | NOT_STARTED

## Fixture Manifest
Fixture ID | File | Kind | Split | Document Type | Currency | Country | Expected Route | Expected Status | Ground Truth | Expected Findings | Notes | SHA-256 | Has Ground Truth
INV-001 | documents/pdf/inv-001_us_office_supplies_with_sales_tax.pdf | visual_pdf | functional | invoice | USD | US | visual_model | ready_for_approval | ground_truth/INV-001.json | expected_findings/INV-001.json | US office supplies with sales tax | 690965410e83325cf79f837fb7dbb574ebf0a1cfa0b776766f880dd0c0b83912 | 1
INV-002 | documents/pdf/inv-002_uk_vat_services_invoice.pdf | visual_pdf | functional | invoice | GBP | GB | visual_model | ready_for_approval | ground_truth/INV-002.json | expected_findings/INV-002.json | UK VAT services invoice | 8a3adc79b9434c88ac97414448b06f6cf4f654b1c6d8652f8697a19ef3feb23c | 1
INV-003 | documents/pdf/inv-003_eu_cross-border_reverse-charge_invoice.pdf | visual_pdf | functional | invoice | EUR | DE | visual_model | ready_for_approval | ground_truth/INV-003.json | expected_findings/INV-003.json | EU cross-border reverse-charge invoice | 44e93f6ea3faa4970bbc94dab3df01c455dca23ec296af14bdb532df254e3841 | 1
INV-004 | documents/pdf/inv-004_india_gst_goods_invoice.pdf | visual_pdf | functional | invoice | INR | IN | visual_model | ready_for_approval | ground_truth/INV-004.json | expected_findings/INV-004.json | India GST goods invoice | 07741f809d40f929fa65b0c2c3c60fa1e99a065b24824a8c7b8718ece2f861ce | 1
INV-005 | documents/pdf/inv-005_japan_jpy_zero-decimal_invoice.pdf | visual_pdf | functional | invoice | JPY | JP | visual_model | ready_for_approval | ground_truth/INV-005.json | expected_findings/INV-005.json | Japan JPY zero-decimal invoice | f4e670a4a0bccb942a3e63bebede02a4b4b7d85c34eda038f785cce425f655b4 | 1
INV-006 | documents/pdf/inv-006_kwd_three-decimal_currency_invoice.pdf | visual_pdf | functional | invoice | KWD | KW | visual_model | ready_for_approval | ground_truth/INV-006.json | expected_findings/INV-006.json | KWD three-decimal currency invoice | b88af361a17358040e4e35bfd2d76c14b0399a483fb76d6eae2f0b9157245d1f | 1
INV-007 | documents/pdf/inv-007_uae_vat_invoice.pdf | visual_pdf | functional | invoice | AED | AE | visual_model | ready_for_approval | ground_truth/INV-007.json | expected_findings/INV-007.json | UAE VAT invoice | e6df96e8e1c14e49ca2289151720b7510fc546c16680a0a258152191ebd8b577 | 1
INV-008 | documents/pdf/inv-008_canada_hst_invoice.pdf | visual_pdf | functional | invoice | CAD | CA | visual_model | ready_for_approval | ground_truth/INV-008.json | expected_findings/INV-008.json | Canada HST invoice | 3f3a6800f91a51fc404fb74d24fc0f5c2fb33e3e216c665ba18d1d067d19344f | 1
INV-009 | documents/pdf/inv-009_eur_credit_note.pdf | visual_pdf | functional | credit_note | EUR | DE | visual_model | ready_for_approval | ground_truth/INV-009.json | expected_findings/INV-009.json | EUR credit note | 22bcb923c3aade01790db1ffa4348036075e4f4068e8e85607efbedeeff7037a | 1
INV-010 | documents/pdf/inv-010_simple_retail_receipt.pdf | visual_pdf | functional | receipt | USD | US | visual_model | ready_for_approval | ground_truth/INV-010.json | expected_findings/INV-010.json | Simple retail receipt | b3acdc49c3937fd097c1036edfc7609341cbd775a1efc2960c8edb7164be7509 | 1
INV-011 | documents/pdf/inv-011_multi-page_line-item_invoice.pdf | visual_pdf | functional | invoice | EUR | DE | visual_model | ready_for_approval | ground_truth/INV-011.json | expected_findings/INV-011.json | Multi-page line-item invoice | adc3e19f8ad6e6f703bdd23548720b14971e90954f4cca0cb2b85a9bb529c125 | 1
INV-012 | documents/pdf/inv-012_invoice_with_allowance_and_charge.pdf | visual_pdf | functional | invoice | GBP | GB | visual_model | ready_for_approval | ground_truth/INV-012.json | expected_findings/INV-012.json | Invoice with allowance and charge | b38261fe267044af54892a422c6d075ebb73cfe02a9b1e01d9fec0336969f787 | 1
INV-013 | documents/pdf/inv-013_mexico_vat_and_withholding_invoice.pdf | visual_pdf | functional | invoice | MXN | MX | visual_model | ready_for_approval | ground_truth/INV-013.json | expected_findings/INV-013.json | Mexico VAT and withholding invoice | 8faef69635fb505f05226fe137e9bdc79c480909666fcc6455657d97a661b8b5 | 1
INV-014 | documents/pdf/inv-014_arithmetic_mismatch_invoice.pdf | visual_pdf | functional | invoice | USD | US | visual_model | needs_review | ground_truth/INV-014.json | expected_findings/INV-014.json | Arithmetic mismatch invoice | b58f3fc0a773fe1ed270abdbb70079f74b819feedc0ad0d07073e06c88d4743c | 1
INV-015 | documents/pdf/inv-015_missing_currency_invoice.pdf | visual_pdf | functional | invoice | UNKNOWN | GB | visual_model | needs_review | ground_truth/INV-015.json | expected_findings/INV-015.json | Missing currency invoice | d765ac21483fdfcb58c64ed6aa00ae511c05a2f8bb18f6c53f02704a1759a02a | 1
INV-016 | documents/pdf/inv-016_ambiguous_invoice_number.pdf | visual_pdf | functional | invoice | AED | AE | visual_model | needs_review | ground_truth/INV-016.json | expected_findings/INV-016.json | Ambiguous invoice number | fe80089c37242abb917ae123db6f71df256d86cec97059ae9e65cc2fe0cf41b3 | 1
INV-017A | documents/pdf/inv-017a_duplicate_candidate_original.pdf | visual_pdf | functional | invoice | CAD | CA | visual_model | ready_for_approval | ground_truth/INV-017A.json | expected_findings/INV-017A.json | Duplicate candidate original | ac9266f0a4fa3af705da93d514a6728dea19b400318d753888192543b6c8b505 | 1
INV-017B | documents/pdf/inv-017b_duplicate_candidate_copy.pdf | visual_pdf | functional | invoice | CAD | CA | visual_model | needs_review | ground_truth/INV-017B.json | expected_findings/INV-017B.json | Duplicate candidate copy | 4494b4824d6d2bd3deeb2980719168e6900e1d9de9560909cb05b62faf6ee7e5 | 1
IMG-001 | documents/images/IMG-001_blurred_low_resolution_scan.jpg | image | functional | invoice | GBP | GB | visual_model | needs_review | ground_truth/IMG-001.json | expected_findings/IMG-001.json | LOW_IMAGE_QUALITY | 6efc473b3a4f5dbacdceb06ba941d10d86362626a0540062ad237a204520fd4c | 1
IMG-002 | documents/images/IMG-002_rotated_90_degrees.png | image | functional | invoice | EUR | DE | visual_model | needs_review | ground_truth/IMG-002.json | expected_findings/IMG-002.json | ROTATION_DETECTED | e6d00f204dc712df8dd2c6cf38b1f867333a6dfd5d2b3906043ea6e55d3f7afd | 1
IMG-003 | documents/images/IMG-003_phone_photo_skew.jpg | image | functional | invoice | INR | IN | visual_model | needs_review | ground_truth/IMG-003.json | expected_findings/IMG-003.json | PERSPECTIVE_SKEW | 2417046f9fc3799d385a4478a59d8a540162354e1323c657bde968732c141e8e | 1
IMG-004 | documents/images/IMG-004_receipt.png | image | functional | receipt | USD | US | visual_model | ready_for_approval | ground_truth/IMG-004.json | expected_findings/IMG-004.json | clean image fixture | edca0c0213c8e824a4ddb990f16242ca1b61c242b2bc40ad508eaeab23ec4ff0 | 1
IMG-005 | documents/images/IMG-005_multipage_invoice.tiff | image | functional | invoice | EUR | DE | visual_model | ready_for_approval | ground_truth/IMG-005.json | expected_findings/IMG-005.json | clean image fixture | c7c5a8d7d78e64f6ab5a97f5072df97cb97e574b369b8e5a505067119306c3a7 | 1
XML-001 | documents/structured/XML-001_synthetic_ubl_invoice.xml | ubl_xml | functional | invoice | EUR | DE | structured_parser | ready_for_approval | ground_truth/XML-001.json | expected_findings/XML-001.json | Synthetic UBL-shaped functional fixture; not an official conformance sample | 11ac33ba2f6bca0b191a9add898459a63c52b4cfdd29ac0b66e3f4608d19d121 | 1
XML-002 | documents/structured/XML-002_unknown_profile.xml | unknown_xml | negative | unknown | UNKNOWN | UNKNOWN | quarantine | quarantined |  | expected_findings/XML-002.json | Unknown XML must not silently fall back to vision | 69b5f9ceee17decf31ca8f2fa3a09ac6257178f8a3d03a55c5dd7ea0abe4e383 | 0
HYB-001 | documents/pdf/HYB-001_hybrid_pdf_with_embedded_ubl.pdf | hybrid_pdf_xml | functional | invoice | EUR | DE | hybrid_compare | ready_for_approval | ground_truth/HYB-001.json | expected_findings/HYB-001.json | PDF with embedded synthetic UBL attachment | 9c97c852769406795953cbc2d29bafd5eacfbbf1577054c2185766e3a5fc00b2 | 1
BAD-001 | documents/unsafe/BAD-001_password_protected.pdf | unsafe_input | negative | unknown | UNKNOWN | UNKNOWN | quarantine | quarantined |  | expected_findings/BAD-001.json | Password-protected PDF must be rejected without password cracking | 1d954e8a7d66e4a80bae2b689ffd5965ab4564a5514701b2db2257c2c26a5398 | 0
BAD-002 | documents/unsafe/BAD-002_truncated_corrupt.pdf | unsafe_input | negative | unknown | UNKNOWN | UNKNOWN | quarantine | quarantined |  | expected_findings/BAD-002.json | Truncated PDF must fail safely | 1e62d09dcf74ed7d9354aab8a185a3268b1cd4387cd426388651380ad6ab9db5 | 0
BAD-003 | documents/unsafe/BAD-003_extension_mismatch.pdf | unsafe_input | negative | unknown | UNKNOWN | UNKNOWN | quarantine | quarantined |  | expected_findings/BAD-003.json | Extension and magic bytes disagree | bfe5b48e6d0901625228e30e96b9eece02626d79593e88d7c990abe5b1076fae | 0

## Model Benchmark
Run ID | Fixture ID | Route | Parser/Model ID | Exact Revision | Quantization | Runtime | Device | Schema Valid? | Supplier Exact? | Invoice No Exact? | Currency Exact? | Payable Exact? | Tax Exact? | Line Count Exact? | Evidence Coverage % | Hallucinated Fields | Latency ms | Peak Memory MB | Repair Used? | Final Status | Notes

## Acceptance Gates
M2.5–M5 Acceptance Gates
Milestone | Gate | Target | Observed | Status
M2.5 | M2 provider contract remains unchanged | Pass |  | OPEN
M2.5 | Synthetic fixtures execute reproducibly | 29 |  | OPEN
M2.5 | Ground-truth fixtures scored | 25 |  | OPEN
M2.5 | Digital PDF and scan/image paths | Pass |  | OPEN
M2.5 | Provenance, latency, p95, memory, failure metrics | Recorded |  | OPEN
M2.5 | Feature-flag rollback to prior M2 provider | Pass |  | OPEN
M3 | 50-document batch completed end to end | Yes |  | OPEN
M3 | Unresolved critical/high finding auto-accepted | 0 |  | OPEN
M3 | Edited high-risk fields with evidence/confirmation | 100% |  | OPEN
M4 | Tenant isolation tests | Pass |  | OPEN
M4 | Deletion verifier failures | 0 |  | OPEN
M4 | Restore drill | Pass |  | OPEN
M5 | Operator time saving | >=50% |  | OPEN
M5 | Unattended high-risk precision | >=99.5% |  | OPEN
M5 | Escaped critical monetary errors | 0 |  | OPEN
M5 | Pilot requests continued use | >=1 |  | OPEN